## Slide 1: Local Food Systems
Southern Region SERA Application

## Slide 2
Requested Duration: October 01, 2016 - September 30, 2021
Administrative Advisors:
  Ed Jones (VA) - Extension
  Eric Young (SAAESD) - Research
Strengthening the Southern Region Extension and Research System to Support Local & Regional Foods Needs and Priorities

## Slide 3: Issues Work Group
Objective: Within 2 years, identify the top 10 pressing issues facing Extension agents in food systems work within the region to direct future Extension and Research activities.

## Slide 4: Strategies
Conduct a literature review
Develop a survey
Conduct survey
Analyze results
Disseminate results

## Slide 5: Learning Communities Work Group
Objective: To create learning communities of land grant professionals from at least 15 land grant universities in the south and local, state, and federal partners around high priority needs in the food system in the next three to five years.

## Slide 6: Strategies
Communicate top 10 issues based on survey
Recruit participants to work on various issues
Help identify work plans
Develop communication platform(s)
Track progress of teams

## Slide 7: Resource Repository Work Group
Objective: Design a user-friendly and robust repository of local foods system resources that meet the needs of Extension and Research professionals in the land-grant system, by 2020, with measurable increases in use and quantity of resources by 20 percent per year.

## Slide 8: Strategies
Inventory existing resources
Contact experts to get them to contribute
Identify gaps in existing resources
Engage people in developing new resources
Create web-based repository to house resources
Develop webinars, commuications package to promote repository and how to use it

## Slide 9: Impact Work Group
Objective: Strengthen capacity of research and extension professionals in the southern region for gathering, communicating, and marketing impact data and analyzing secondary data through identification and sharing of common measures, resources and tools by reporting on an annual basis.

## Slide 10: Strategies
Develop a common set of measures
Gain commitment from Extension to gather data
Analyze data
Report findings

## Slide 11: Organizational Structures Work Group
Objective: Identify processes, collaborative behavior, staffing, and organizational structures of land-grant universities participating in the development of local food systems. Collect data annually from state SERA liaisons and create a regional data bank and series of case studies by 2019.

## Slide 12: Strategies
Create a timeline of expected deliverables
Coordinate with other work groups
Identify core metric for assessing resources
Develop an instrument for capturing qualitative/quantitative data
Coordinate and analyze data
Design case study structure and recruit authors
Develop communication strategy